## Sheet1
DEFAULT DRAWDOWN SCHEDULES FOR NZ ON AIR FUNDING
Short form series (i.e. Web series / Game / App) | Proposed | Reports | Example NZOA funding | 100000
Execution, platform contract | 30% | 0 | 30000
Game/app: Pre production, design approval Webseries: Production | 25% | 1 | 25000
Game/app: Approval of beta version by NZOA and platform. Webseries: Offline approval | 20% | 1 | 20000
Delivery to platform, or public launch | 20% | 1 | 20000
Final cost report | 5% | 1 | 5000
| 100% | 4 | 100000
Documentary one-off/short-run (i.e. 3 eps) | Proposed | Reports | Example NZOA funding | 150000
Execution | 15% | 0 | 22500
Commencement of pre-production | 15% | 1 | 22500
Commencement of principal photography | 25% | 1 | 37500
Commencement of post-production (off-line edit) | 20% | 1 | 30000
Offline approval | 15% | 1 | 22500
Full delivery | 5% | 0 | 7500
Final cost report | 5% | 1 | 7500
| 100% | 5 | 150000
Documentary series (e.g. 6 eps plus) | Proposed | Reports | Example NZOA funding | 200000
Execution | 15% | 0 | 30000
Commencement of pre-production | 15% | 1 | 30000
Commencement of principal photography | 25% | 1 | 50000
Commencement of post-production (off-line edit) | 20% | 1 | 40000
Offline approval 1 ep | 10% | 1 | 20000
Offline approval all eps | 5% | 1 | 10000
Full delivery | 5% | 0 | 10000
Final cost report | 5% | 1 | 10000
| 100% | 6 | 200000
Drama one-off/short-run (i.e. 3 eps) | Proposed | Reports | Example NZOA funding | 1000000
Execution | 10% | 0 | 100000
Commencement of pre-production | 20% | 1 | 200000
Commencement of principal photography | 30% | 1 | 300000
Commencement of post-production (off-line edit) | 20% | 1 | 200000
Offline approval | 10% | 1 | 100000
Full delivery | 5% | 0 | 50000
Final cost report | 5% | 1 | 50000
| 100% | 5 | 1000000 | 0
Drama series (i.e. 6 eps plus) | Proposed | Reports | Example NZOA funding | 5000000
Execution | 8% | 0 | 400000
Commencement of pre-production | 15% | 1 | 750000
Commencement of principal photography (divided up evenly into number of shooting blocks, e.g. 5) | 10% | 1 | 500000
Commencement of principal photography (2nd block) | 10% | 1 | 500000
Commencement of principal photography (3rd block) | 10% | 1 | 500000
Commencement of principal photography (4th block) | 10% | 1 | 500000
Commencement of principal photography (5th block) | 10% | 1 | 500000
Offline approval 1 ep | 12% | 1 | 600000
Offline approval half eps | 5% | 1 | 250000
Offline approval all eps | 5% | 1 | 250000
Full delivery | 2.5% | 0 | 125000
Final cost report | 2.5% | 1 | 125000
| 100% | 10 | 5000000
Entertainment one-off e.g. live OB | Proposed | Reports | Example NZOA funding | 150000
Execution | 10% | 0 | 15000
Commencement of pre-production | 20% | 1 | 30000
Commencement of production/post-production | 50% | 1 | 75000
Full delivery/transmission | 15% | 0 | 22500
Final cost report | 5% | 1 | 7500
| 100% | 3 | 150000
Children's/magazine weekly series | Proposed | Reports | Example NZOA funding | 1500000
Execution | 7.5% | 0 | 112500
Commencement of pre-production | 7.5% | 1 | 112500
Commencement of principal photography (divided up evenly into months, e.g. 10) | 7.5% | 1 | 112500
Transmission of 1/10 series | 7.5% | 1 | 112500
Transmission of 2/10 eps | 7.5% | 1 | 112500
Transmission of 3/10 series | 7.5% | 1 | 112500
Transmission of 4/10 series | 7.5% | 1 | 112500
Transmission of 5/10 series | 7.5% | 1 | 112500
Transmission of 6/10 series | 7.5% | 1 | 112500
Transmission of 7/10 series | 7.5% | 1 | 112500
Transmission of 8/10 series | 7.5% | 1 | 112500
Transmission of 9/10 series | 7.5% | 1 | 112500
Full delivery/transmission | 7.5% | 0 | 112500
Final cost report | 2.5% | 1 | 37500
| 100% | 12 | 1500000
Development | Proposed | Reports | Example NZOA funding | 10000
Execution, writers contracts, platform contracts | 50% | 0 | 5000
Final cost report | 50% | 1 | 5000
| 100% | 1 | 10000
Notes
1. Reports required for all but execution and delivery drawdown.
2. Condition precedent to pre-production drawdown would be copy of broadcaster/platform agreement & funding agreements
If there is a delay in the broadcaster's agreement we are happy to discuss varying this drawdown, but this means we get wind of any delay earlier.
3. Condition precedent to principal photography is Health and Safety confirmations.
4. Commencement of post-production refers to the off-line editor starting (not simply data ingest).
5. Note that full delivery means all deliverables required by platform e.g. music returns etc.
6. Final cost report, also a copy of the finished programme, stats reports, diversity report etc.